## Sheet1
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Score | Mitigation Strategy | Contingency Plan | Status
R-01 | Gemini API rate limits affect testing | Technical | 4 | 3 | 12 | Implement response caching | Switch to local LLM fallback | Active
R-02 | Generated configs contain security vulnerabilities | Technical | 2 | 5 | 10 | Validate against CCNA security checklist | Add security scanning layer | Active
R-03 | API key security exposure in GitHub | Security | 3 | 3 | 9 | Use .env files, and add .gitignore rules | Regenerate API key if exposed | Mitigated
R-04 | Insufficient testing coverage | Quality | 2 | 4 | 8 | Create test plan with 20+ scenarios | Conduct peer review | Active
R-05 | Documentation incomplete for portfolio | PM | 3 | 2 | 6 | Dedicate final phase to documentation | Prioritize README and PM artifacts | Active